# TECHNICAL SPECIFICATION BLUEPRINT: DOCUMENT 5

## AGILE SPRINT PLAN & WORK BREAKDOWN STRUCTURE (WBS)

Project: Enterprise Human Resource Management System (HRMS)

Development Timeline: 6 Months (24 Weeks / 12 Sprints)

Sprint Duration: 2 Weeks (10 Working Days per Sprint)

Core Target Architecture: Phased Feature Delivery Pipeline

## 1. AGILE ROLES & SPRINT MECHANICS

To execute this massive scope with a lean development team (1 Lead Full-Stack Engineer, 1 Backend DRF Engineer, 1 Frontend React Engineer), the team must adhere to the following sprint delivery schedule:

- Day 1: Sprint Planning & Task Allocation. Estimate individual sub-tasks in story points. Backlog items are broken down until no single development task exceeds 3 days of effort.

- Days 2–9: Active Development & Daily Standup. Daily 15-minute syncs to identify blockers. Code is committed in small, isolated feature branches, triggering automatic testing pipelines.

- Day 10: Sprint Review & Retrospective. Live demonstrations of the working software increment built during the sprint. Code is merged into the staging branch only after passing QA validation.

## 2. THE 12-SPRINT DEVELOPMENT SCHEDULE

### 🚀 PHASE 1: CORE FOUNDATION & RBAC ARCHITECTURE (MONTHS 1–2)

#### Sprint 1: System Baseline, Session Architecture & Identity Management

- Backend Tasks:

  - Initialize the Django REST Framework project with production-grade environment configurations.

  - Set up the PostgreSQL database cluster and run the foundational master lookup schemas (system_roles, company_structures).

  - Implement JWT stateless authentication endpoints integrated with corporate AD/LDAP simulation logic and local database fallback routines.

  - Deploy the Redis storage broker and implement token revocation logic via /api/v1/auth/logout/ using structural token identifiers (jti).

- Frontend Tasks:

  - Scaffold the React Vite application structure, configure routing guards, and install the Tailwind CSS UI component framework.

  - Create user login layouts featuring comprehensive global error boundary state management and integration handlers for token refresh loops.

#### Sprint 2: Core HR Master Registry & Security Layer (SOW Module 4.1)

- Backend Tasks:

  - Build CRUD endpoints for the primary employee table (employees) and documents mapping layer (employee_documents).

  - Implement the application-layer symmetric AES-256 field-level encryption system to protect sensitive PII inputs (Bank details, National IDs).

  - Deploy a login throttling middleware that tracks failed login attempts and flags is_locked_out to TRUE for 30 minutes after 5 continuous validation failures.

  - Implement the custom Django database middleware layer to capture changes in an append-only historical audit ledger.

- Frontend Tasks:

  - Build the Employee Profile Grid Console interface.

  - Create multi-tab forms with real-time schema validation for capturing employee personal master fields, including front-end digit masking filters for sensitive identifiers.

#### Sprint 3: Organization Hierarchy & Self-Service Portals (SOW Modules 4.2 & 4.11)

- Backend Tasks:

  - Implement the dynamic self-referencing relationship query structure to handle complex organizational matrix reporting lines (reporting_manager_id).

  - Build structural constraint validation logic that automatically blocks manual hiring requests if the target department meets its budget ceiling.

- Frontend Tasks:

  - Render the interactive visual Organization Hierarchy tree component using React.

  - Deliver the base layouts for the Employee Self-Service (ESS) and Manager Self-Service (MSS) operational dashboards, mapping layout components dynamically based on JWT role contents.

### ⏱️ PHASE 2: OPERATIONAL TIME & LEAVE MANAGEMENT (MONTHS 3–4)

#### Sprint 4: Roster Controls & Biometric Data Ingestion (SOW Module 4.5)

- Backend Tasks:

  - Design the database tables for tracking shift rotations (shift_patterns, employee_rosters), explicitly coding logic to calculate cross-midnight overnight shift boundaries.

  - Build the secure /api/v1/attendance/punch/ endpoint to ingest batch data uploads from on-premise biometric listener devices via localized API-Key header checks.

- Frontend Tasks:

  - Create UI grid components for line managers to manage shift schedules and assign team rosters dynamically.

  - Integrate browser geo-tracking APIs with backend location validation checks to support mobile check-in features.

#### Sprint 5: Automated Time Card Processing & Regularization (SOW Module 4.5)

- Backend Tasks:

  - Develop asynchronous Celery tasks to process raw device check-in logs and calculate anomalies (late entries, early logouts, overtime calculations) mapped to the shift's initiating calendar date.

  - Build workflows and endpoint tracks to process attendance correction requests.

- Frontend Tasks:

  - Build detailed time card timeline interfaces showing daily calculated work hours and shift validation metrics.

  - Create self-service request forms for submitting attendance correction requests.

#### Sprint 6: Policy-Driven Leave Management Engine (SOW Module 4.6)

- Backend Tasks:

  - Build the structural engine for managing complex time-off rules, tracking dynamic monthly leave balance allocations, accrual rates, and carry-forward limits.

  - Develop multi-level request routing engines that trigger automated email notifications to managers.

- Frontend Tasks:

  - Develop request interfaces for employees to apply for leaves, complete with dynamic attachment upload options.

  - Design shared team calendar components for managers to track active time-off requests within their team to prevent schedule clashes.

### 💰 PHASE 3: FINANCIAL RUNTIMES & STATUTORY ENGINE (MONTHS 4–5)

#### Sprint 7: Core Payroll Formula Interpreter (SOW Module 4.7)

- Backend Tasks:

  - Create a secure calculation utility to parse mathematical string expressions for custom salary items (Basic, HRA, PF allowances).

  - Implement an integration pipeline that automatically injects unpaid absences (Loss of Pay days) from the attendance module into the active payroll cycle.

- Frontend Tasks:

  - Design the central corporate Payroll Structure Control Panel interface for HR Administrators.

#### Sprint 8: Statutory Localization & Disbursement Workflows (SOW Module 4.7)

- Backend Tasks:

  - Develop automated compliance calculation scripts to handle regional statutory requirements (Provident Fund ECR layouts, ESIC text generators, income tax brackets).

  - Configure background Celery workers to batch-process salaries for up to 5,000 employees concurrently.

  - Implement automated scripts to export formatted payment instruction documents directly to secure SFTP targets.

- Frontend Tasks:

  - Create a centralized Payroll Processing Console dashboard featuring step-by-step progress bars and validation simulation screens.

  - Build secure interfaces for employees to view and download monthly digital payslips.

#### Sprint 9: Travel Logistics & Expense Management (SOW Module 4.12)

- Backend Tasks:

  - Create validation modules that check submitted expense totals against corporate policy spending caps based on employee grade bands.

  - Design database infrastructure to attach file uploads directly to submitted financial lines.

- Frontend Tasks:

  - Build self-service expense reporting forms with integrated camera components for uploading digital receipts.

### 🎯 PHASE 4: TALENT LIFECYCLE, INSIGHTS, & VAPT LOGISTICS (MONTHS 5–6)

#### Sprint 10: Recruitment (ATS) & Performance Frameworks (SOW Modules 4.3 & 4.9)

- Backend Tasks:

  - Build the database tables and business logic for tracking candidate hiring pipelines, scheduling panel reviews, and managing internal job applications.

  - Build database structures for the performance module, processing objective settings (employee_goals) and appraisal tracking reviews (performance_reviews) mapped to bell-curve calibration targets.

- Frontend Tasks:

  - Create comprehensive candidate pipeline trackers using interactive drag-and-drop board layouts.

  - Build self-service goal tracking setups and manager appraisal review input forms.

#### Sprint 11: Training Portal (LMS), Asset Tracking, & Helpdesk (SOW Modules 4.10, 4.13, & 4.14)

- Backend Tasks:

  - Deploy automated background tasks to scan the documents table and send automated expiration notifications 90, 60, and 30 days out.

  - Build tables for tracking LMS course tracking bundles (courses, training_enrollments) supporting SCORM storage parsing.

  - Build asset assignment tables linked directly to the exit clearance workflow engine.

  - Build encrypted messaging frameworks to isolate sensitive helpdesk tickets and grievance cases.

- Frontend Tasks:

  - Build the unified internal helpdesk ticketing workspace interface.

  - Build course navigation viewer grids for employee training programs.

#### Sprint 12: Business Intelligence Analytics, VAPT Hardening, & Go-Live (SOW Modules 4.17 & 4.18)

- Backend Tasks:

  - Optimize query latency for complex reporting metrics (headcount timelines, attrition rates) by executing the pre-defined database indexes.

  - Perform system-wide security hardening based on OWASP Top 10 guidelines and run the deployment automation scripts inside the on-premise staging cluster.

- Frontend Tasks:

  - Create the primary executive dashboard using analytical chart libraries to visualize key operational metrics.

## 3. WORK BREAKDOWN STRUCTURE (WBS) LEVEL-3 DICTIONARY

To help your project managers organize your tracking boards (Jira or Linear), use this hierarchical breakdown to map individual tasks directly to developer assignments:

1.0 FOUNDATION_&_AUTH_ENGINE

1.1 SETUP_ENV: Initialize Django REST Framework and configure production project files.

1.2 BUILD_RBAC: Deploy database permissions schema and configure JWT auth guards.

1.3 SESSION_REDIS: Build token revocation models and Redis-backed blacklisting handlers.

1.4 LOCKOUT_SHIELD: Deploy brute-force defense limits and failed login throttling.

2.0 CORE_HR_MODULE

2.1 REGISTRY_CRUD: Build endpoints for employee data management and setup state models.

2.2 CRYPTO_PII: Deploy symmetric AES-256 field encryption mechanisms at the ORM layer.

2.3 AUDIT_LEDGER: Implement database triggers to log changes to data elements.

3.0 ATTENDANCE_&_ROSTERS

3.1 INGEST_LOGS: Build ingestion systems to process biometric device punch records.

3.2 OVERNIGHT_ROSTER: Develop calendar shift matrices and pattern validation logic for cross-midnight schedules.

3.3 ANOMALY_WORKER: Deploy background tasks to flag attendance anomalies daily.

4.0 PAYROLL_BATCH

4.1 RUNTIME_CALC: Develop the mathematical string formula interpretation parser.

4.2 DEDUCT_LOCAL: Build regional compliance calculation scripts (PF/ESIC/PT).

4.3 SFTP_BANK: Deploy file compression utilities and secure SFTP transfer tools.

5.0 PMS_&_LMS_MODULES

5.1 GOALS_OKR: Deploy endpoints and schemas for tracking objectives and weightage maps.

5.2 REVIEW_CALIB: Design calibration panels for processing bell-curve evaluations.

5.3 COURSE_SCORM: Build structures supporting e-learning progress and package tracking.